## Sheet1
" | Activity | Task | Remarks | Status | ETA | Start date | End date
1 | Initial Research | Identify common tasks in NLP Identify data analysis done as part of most NLP projects Identify text preprocessing/cleaning activities done | Arun to guide | Completed | 2022-08-07 | 2022-08-03 | 2022-08-06
2 | Design | (1) design patterns for each of the tasks (2) data input format to be finalized |  | Completed
3 | Data collection | Shortlist few text related datasets from Kaggle or other data sources |  | Completed
4 | Build | Modularized functions for
|  | (a) Reading the dataset |  | Completed
|  | (b) Text analysis and profiling |  | Completed
|  | (c) Text pre processing and cleasning |  | Completed
|  | (d) Text operations like tokenization , stemming/lemmatization , stop words ( custom and default) |  | Completed
(e) topic modeling
|  | (f) NER |  | Completed
5 | Integrate | Combine the various modules in a wrapper Streamlit UI for demo

## Sheet2
Data Collection |  | Function Name | Class Name/Lib | Purpose | Comments
| Spam/Ham Dataset |  |  | For Performing Operations on the Dataset
Modularized Function
| Reading Dataset | files.upload() | google.colab -> files | Reading the Dataset
|  | csv_input() |  | Reading the file from the File Input
json_input()
| Basic Visualization | data_head() |  | Basic Visualization on the Dataset
info_print()
describe_print()
dtype_print()
data_visualization()
| Null Value Visualization | null_values() |  | Visualize the Null Values present in Dataset
missing_values()
msno_bargraph()
msno_heatmap()
|  | null_val_rows() |  | Remove Null Values from the Dataset
del_col_null()
row_null
drop_duplicate_rows
| Standard Pre - Processing | stnd_prepro |  | Perform Pre-Processing on the Data
removedigits()
removealphabets()
removealphanum()
onlyalphanum()
enter_regex()
remove_special()
Clean()
| Encoding | ftfy() |  | Fix Encoding Issues
| Language Detection | detect() | langdetect | For detecting the language of the text
|  | value_counts().plot() |  | Visualizing the language
| Language Translation | translate() | Translator | For translating the languages to a particular language
| Word Cloud Visualization |  | WordCloud | For representing Stop Words as a Word Cloud